## Purchase summary
MP Adams Plot 4, Eckington - Procurement C02
Client MP Adams. All quantities include waste per P-06; each purchase split by section below.
Group | Purchase item | Unit | Order qty | Sections
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | 27 | GF temporary bracing: 13; FF temporary bracing: 8; Gable temporary bracing: 6
Timber | 35x89 C16 @ 4.8m | lengths | 2 | GF panels: 2
Timber | 36x89 C16 @ 4.8m | lengths | 2 | GF panels: 2
Timber | 38x140 C16 @ 4.8m | lengths | 355 | GF sole plates: 15; GF head binder: 15; FF head binder: 10; GF panels: 164; FF panels: 103; Gable panels: 48
Timber | 38x87 C16 @ 4.8m | lengths | 2 | FF panels: 2
Timber | 38x89 C16 @ 4.8m | lengths | 168 | GF sole plates: 7; GF head binder: 4; GF temporary bracing: 5; FF temporary bracing: 3; Gable temporary bracing: 3; GF window battens: 9; FF window battens: 4; GF panels: 60; FF panels: 73
Timber | 45x145 C24 @ 4.8m | lengths | 23 | GF panels: 13; FF panels: 10
Timber | 45x195 C24 @ 4.8m | lengths | 12 | First floor edgebinder: 9; First floor edgebinder rips: 3
Timber | 45x220 C16 @ 4.8m | lengths | 9 | GF panels: 9
Engineered beams | Glulam 100x240 GL24h @ 1878mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 2076mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 3414mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 3482mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 3576mm | no. | 1 | First floor beams: 1
Engineered beams | Glulam 100x240 GL24h @ 629mm | no. | 1 | First floor beams: 1
Sheet materials | Egger P5 22mm flooring 600x2400 | sheets | 55 | First floor deck: 55
Sheet materials | Marine ply 14mm 1220x2440 | sheets | 1 | First floor beams: 1
Sheet materials | OSB/3 9mm 1197x2397 | sheets | 113 | First floor waist band: 5; GF panels: 50; GF loose internal sheathing: 6; FF panels: 31; Gable panels: 21
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | 3 | GF panels: 2; FF panels: 1
Insulation | PIR 120mm 1200x2400 | boards | 74 | GF panels: 33; FF panels: 23; Gable panels: 18
Membranes | Breather membrane 100m x 2.7m roll | rolls | 2 | GF panels: 0.48; FF panels: 0.32; Gable panels: 0.26; First floor waist band: 0.07
Membranes | DPC 300mm x 30m roll | rolls | 1 | GF sole plates: 1
Membranes | DPC 600mm x 30m roll | rolls | 3 | GF sole plates: 3
Metalwork | Simpson Strong-Tie ETFSS timber frame holding-down strap | no. | 19 | GF holding-down: 19
Fixings | 3.1x50mm coil nails (box of 2,500) | boxes | 4 | GF panels: 1.72; GF loose internal sheathing: 0.21; FF panels: 0.95; Gable panels: 0.76
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | 4 | GF panels: 2.02; FF panels: 1.56; Gable panels: 0.33
Fixings | Brick ties (box of 250) | boxes | 5 | External walls GF + FF + gables: 4.2
Fixings | M7.5x100 concrete screw (box of 100) | boxes | 3 | GF sole plates: 1.72; GF temporary bracing: 0.53
Sealants & adhesives | D4 adhesive 1L | bottles | 9 | First floor deck: 8.46
Sealants & adhesives | Silicone sealant 280ml | tubes | 10 | GF sole plates: 9.19

## By section
Group | Purchase item | Unit | Section | Net qty | Order qty (with waste) | Basis | Drawing | Note
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | GF temporary bracing | 12 | 13 | 24 x 2.7m braces, 2 per 5.4m, +5% | P4-GA-01
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | FF temporary bracing | 7 | 8 | 14 x 2.7m braces, 2 per 5.4m, +5% | P4-GA-02
Timber | 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths | Gable temporary bracing | 5 | 6 | 9 x 2.7m braces, 2 per 5.4m, +5% | P4-GA-03
| TOTAL 25x100 (4x1) green/brown treated rough-sawn @ 5.4m | lengths |  |  | 27
Timber | 35x89 C16 @ 4.8m | lengths | GF panels | 1 | 2 | 1 pcs / 2.3m -> 1 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture GF
| TOTAL 35x89 C16 @ 4.8m | lengths |  |  | 2
Timber | 36x89 C16 @ 4.8m | lengths | GF panels | 1 | 2 | 1 pcs / 2.3m -> 1 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture GF
| TOTAL 36x89 C16 @ 4.8m | lengths |  |  | 2
Timber | 38x140 C16 @ 4.8m | lengths | GF sole plates | 14 | 15 | 23 pcs / 62.1m -> 14 x 4.8m cut-optimised (3mm kerf) +5% | P4-SP-01
Timber | 38x140 C16 @ 4.8m | lengths | GF head binder | 14 | 15 | 22 pcs / 62.1m -> 14 x 4.8m cut-optimised (3mm kerf) +5% | P4-GA-01
Timber | 38x140 C16 @ 4.8m | lengths | FF head binder | 9 | 10 | 12 pcs / 36.8m -> 9 x 4.8m cut-optimised (3mm kerf) +5% | P4-GA-02
Timber | 38x140 C16 @ 4.8m | lengths | GF panels | 156 | 164 | 441 pcs / 729.6m -> 156 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture GF
Timber | 38x140 C16 @ 4.8m | lengths | FF panels | 98 | 103 | 274 pcs / 451.8m -> 98 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture FF
Timber | 38x140 C16 @ 4.8m | lengths | Gable panels | 45 | 48 | 141 pcs / 211.0m -> 45 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture Gable
| TOTAL 38x140 C16 @ 4.8m | lengths |  |  | 355
Timber | 38x87 C16 @ 4.8m | lengths | FF panels | 1 | 2 | 1 pcs / 2.3m -> 1 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture FF
| TOTAL 38x87 C16 @ 4.8m | lengths |  |  | 2
Timber | 38x89 C16 @ 4.8m | lengths | GF sole plates | 6 | 7 | 7 pcs / 21.3m -> 6 x 4.8m cut-optimised (3mm kerf) +5% | P4-SP-01
Timber | 38x89 C16 @ 4.8m | lengths | GF head binder | 3 | 4 | 3 pcs / 9.6m -> 3 x 4.8m cut-optimised (3mm kerf) +5% | P4-GA-01
Timber | 38x89 C16 @ 4.8m | lengths | GF temporary bracing | 4 | 5 | 24 pcs / 14.4m -> 4 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P4-GA-01
Timber | 38x89 C16 @ 4.8m | lengths | FF temporary bracing | 2 | 3 | 14 pcs / 8.4m -> 2 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P4-GA-02
Timber | 38x89 C16 @ 4.8m | lengths | Gable temporary bracing | 2 | 3 | 9 pcs / 5.4m -> 2 x 4.8m cut-optimised (3mm kerf) +5%; 600 bracing noggins | P4-GA-03
Timber | 38x89 C16 @ 4.8m | lengths | GF window battens | 8.5 | 9 | 51 battens / 72.5m of 38x43 -> 18 x 4.8m 38x43 (+5%), ripped 2 per 38x89 | P4-GA-01
Timber | 38x89 C16 @ 4.8m | lengths | FF window battens | 3.5 | 4 | 28 battens / 32.1m of 38x43 -> 8 x 4.8m 38x43 (+5%), ripped 2 per 38x89 | P4-GA-02
Timber | 38x89 C16 @ 4.8m | lengths | GF panels | 57 | 60 | 185 pcs / 264.3m -> 57 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture GF
Timber | 38x89 C16 @ 4.8m | lengths | FF panels | 69 | 73 | 245 pcs / 321.5m -> 69 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture FF
| TOTAL 38x89 C16 @ 4.8m | lengths |  |  | 168
Timber | 45x145 C24 @ 4.8m | lengths | GF panels | 12 | 13 | 47 pcs / 50.2m -> 12 x 4.8m cut-optimised (3mm kerf) +5%; 7 ripped to 41x145 | Manufacture GF
Timber | 45x145 C24 @ 4.8m | lengths | FF panels | 9 | 10 | 35 pcs / 37.2m -> 9 x 4.8m cut-optimised (3mm kerf) +5%; 7 ripped to 41x145 | Manufacture FF
| TOTAL 45x145 C24 @ 4.8m | lengths |  |  | 23
Timber | 45x195 C24 @ 4.8m | lengths | First floor edgebinder | 8 | 9 | 11 edgebinders / 35.2m cut-optimised +5% | P4-FL-01
Timber | 45x195 C24 @ 4.8m | lengths | First floor edgebinder rips | 3 | 3 | 45x59 rips 9 x 4.8m (+5%), 3 per 45x195 | P4-FL-01
| TOTAL 45x195 C24 @ 4.8m | lengths |  |  | 12
Timber | 45x220 C16 @ 4.8m | lengths | GF panels | 8 | 9 | 9 pcs / 23.0m -> 8 x 4.8m cut-optimised (3mm kerf) +5% | Manufacture GF
| TOTAL 45x220 C16 @ 4.8m | lengths |  |  | 9
Engineered beams | Glulam 100x240 GL24h @ 1878mm | no. | First floor beams | 1 | 1 | GL6 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 1878mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 2076mm | no. | First floor beams | 1 | 1 | GL1 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 2076mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 3414mm | no. | First floor beams | 1 | 1 | GL5 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 3414mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 3482mm | no. | First floor beams | 1 | 1 | GL4 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 3482mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 3576mm | no. | First floor beams | 1 | 1 | GL2 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 3576mm | no. |  |  | 1
Engineered beams | Glulam 100x240 GL24h @ 629mm | no. | First floor beams | 1 | 1 | GL3 | P4-FL-01 | Cut to length
| TOTAL Glulam 100x240 GL24h @ 629mm | no. |  |  | 1
Sheet materials | Egger P5 22mm flooring 600x2400 | sheets | First floor deck | 51.1 | 55 | 73.6 m2 laid, +7.5% | P4-FL-01
| TOTAL Egger P5 22mm flooring 600x2400 | sheets |  |  | 55
Sheet materials | Marine ply 14mm 1220x2440 | sheets | First floor beams | 0.64 | 1 | 6 packers / 15.1m of 100 strip on top of 240 GL = 254 (D-25); 11 strips per sheet, +7.5% | P4-FL-01
| TOTAL Marine ply 14mm 1220x2440 | sheets |  |  | 1
Sheet materials | OSB/3 9mm 1197x2397 | sheets | First floor waist band | 3.75 | 5 | 15 x 290 strips, 4 per sheet, +7.5% | P4-FL-01
Sheet materials | OSB/3 9mm 1197x2397 | sheets | GF panels | 50 | 50 | 105 pieces / 133.2 m2 nested on 50 sheets (P4-CP-OSB, 2mm kerf); exact waste 10.2 m2 incl. 4 reusable offcuts; no % allowance (D-28) | Manufacture GF / P4-CP-OSB
Sheet materials | OSB/3 9mm 1197x2397 | sheets | GF loose internal sheathing | 5.43 | 6 | 13 site-cut pieces / 15.6 m2 on 6 panels (L); full sheets, +7.5% (LS-01) | P4-GA-01 | Sent loose to site
Sheet materials | OSB/3 9mm 1197x2397 | sheets | FF panels | 31 | 31 | 57 pieces / 77.1 m2 nested on 31 sheets (P4-CP-OSB, 2mm kerf); exact waste 11.8 m2 incl. 4 reusable offcuts; no % allowance (D-28) | Manufacture FF / P4-CP-OSB
Sheet materials | OSB/3 9mm 1197x2397 | sheets | Gable panels | 21 | 21 | 51 pieces / 50.9 m2 nested on 21 sheets (P4-CP-OSB, 2mm kerf); exact waste 9.3 m2 incl. 7 reusable offcuts; no % allowance (D-28) | Manufacture Gable / P4-CP-OSB
| TOTAL OSB/3 9mm 1197x2397 | sheets |  |  | 113
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | GF panels | 1.05 | 2 | 9 end cap strips / 3.1 m2, +7.5% | Manufacture GF
Sheet materials | Plywood 9mm 1220x2440 (panel end caps) | sheets | FF panels | 0.69 | 1 | 6 end cap strips / 2.0 m2, +7.5% | Manufacture FF
| TOTAL Plywood 9mm 1220x2440 (panel end caps) | sheets |  |  | 3
Insulation | PIR 120mm 1200x2400 | boards | GF panels | 33 | 33 | 224 pieces / 88.2 m2 nested on 33 boards (P4-CP-PIR, 2mm kerf); exact waste 6.8 m2; no % allowance (D-28); external walls only (P-11) | Manufacture GF / P4-CP-PIR
Insulation | PIR 120mm 1200x2400 | boards | FF panels | 23 | 23 | 148 pieces / 59.6 m2 nested on 23 boards (P4-CP-PIR, 2mm kerf); exact waste 6.6 m2; no % allowance (D-28); external walls only (P-11) | Manufacture FF / P4-CP-PIR
Insulation | PIR 120mm 1200x2400 | boards | Gable panels | 18 | 18 | 86 pieces / 43.1 m2 nested on 18 boards (P4-CP-PIR, 2mm kerf); exact waste 8.8 m2; no % allowance (D-28); external walls only (P-11) | Manufacture Gable / P4-CP-PIR
| TOTAL PIR 120mm 1200x2400 | boards |  |  | 74
Membranes | Breather membrane 100m x 2.7m roll | rolls | GF panels | 0.46 | 0.48 | 117.6 m2 external panel face, 150 laps, +5% | Manufacture GF
Membranes | Breather membrane 100m x 2.7m roll | rolls | FF panels | 0.3 | 0.32 | 77.1 m2 external panel face, 150 laps, +5% | Manufacture FF
Membranes | Breather membrane 100m x 2.7m roll | rolls | Gable panels | 0.25 | 0.26 | 63.4 m2 external panel face, 150 laps, +5% | Manufacture Gable
Membranes | Breather membrane 100m x 2.7m roll | rolls | First floor waist band | 0.06 | 0.07 | 15 x 450 strips (222 per roll) | P4-FL-01
| TOTAL Breather membrane 100m x 2.7m roll | rolls |  |  | 2
Membranes | DPC 300mm x 30m roll | rolls | GF sole plates | 0.83 | 1 | 21.3m + 12 laps x 300 = 24.9m, +5% | P4-SP-01
| TOTAL DPC 300mm x 30m roll | rolls |  |  | 1
Membranes | DPC 600mm x 30m roll | rolls | GF sole plates | 2.41 | 3 | 62.1m + 17 laps x 600 = 72.3m, +5% | P4-SP-01
| TOTAL DPC 600mm x 30m roll | rolls |  |  | 3
Metalwork | Simpson Strong-Tie ETFSS timber frame holding-down strap | no. | GF holding-down | 19 | 19 | 19 positions, engineer 26-431-S-0010 Detail 1 | P4-GA-01 | Fixings to Simpson guidance
| TOTAL Simpson Strong-Tie ETFSS timber frame holding-down strap | no. |  |  | 19
Fixings | 3.1x50mm coil nails (box of 2,500) | boxes | GF panels | 3915 | 1.72 | 3915 OSB coil nails (@150 edges / 300 field) +10% | Manufacture GF
Fixings | 3.1x50mm coil nails (box of 2,500) | boxes | GF loose internal sheathing | 488 | 0.21 | 488 OSB coil nails @150 edges / 300 field +10% (P-11a) | P4-GA-01
Fixings | 3.1x50mm coil nails (box of 2,500) | boxes | FF panels | 2164 | 0.95 | 2164 OSB coil nails (@150 edges / 300 field) +10% | Manufacture FF
Fixings | 3.1x50mm coil nails (box of 2,500) | boxes | Gable panels | 1716 | 0.76 | 1716 OSB coil nails (@150 edges / 300 field) +10% | Manufacture Gable
| TOTAL 3.1x50mm coil nails (box of 2,500) | boxes |  |  | 4
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | GF panels | 4583 | 2.02 | 4583 nails (joints x3, multi-ply @150) +10% | Manufacture GF
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | FF panels | 3551 | 1.56 | 3551 nails (joints x3, multi-ply @150) +10% | Manufacture FF
Fixings | 90mm ring-shank nails (box of 2,500) | boxes | Gable panels | 740 | 0.33 | 740 nails (joints x3, multi-ply @150) +10% | Manufacture Gable
| TOTAL 90mm ring-shank nails (box of 2,500) | boxes |  |  | 4
Fixings | Brick ties (box of 250) | boxes | External walls GF + FF + gables | 955 | 4.2 | 258.2 m2 net external wall x 3.7/m2 +10% | P-21
| TOTAL Brick ties (box of 250) | boxes |  |  | 5
Fixings | M7.5x100 concrete screw (box of 100) | boxes | GF sole plates | 156 | 1.72 | 156 screws +10% | P4-SP-01
Fixings | M7.5x100 concrete screw (box of 100) | boxes | GF temporary bracing | 48 | 0.53 | 48 screws (2 per noggin) +10% | P4-GA-01
| TOTAL M7.5x100 concrete screw (box of 100) | boxes |  |  | 3
Sealants & adhesives | D4 adhesive 1L | bottles | First floor deck | 8.46 | 8.46 | 1L per 6.5 sheets | P4-FL-01
| TOTAL D4 adhesive 1L | bottles |  |  | 9
Sealants & adhesives | Silicone sealant 280ml | tubes | GF sole plates | 8.36 | 9.19 | 156 holes x 15ml = 2.34L +10% | P4-SP-01
| TOTAL Silicone sealant 280ml | tubes |  |  | 10

## Rules
P-06 | Linear timber cut-optimised into 4.8m stock (3mm kerf) then +5%; sheets +7.5%; PIR +10%; fixings, silicone, glue +10% rounded up to purchase units; DPC and membrane laps + 5%, rounded up to rolls.
D-28 | Panel OSB and PIR are ordered at the exact nested sheet count from the cutting packs (2mm kerf, D-27): the waste is known, so no percentage is added.
P-07 | All timber in 4.8m lengths; anything over 4.8m flagged as a special.
P-08 | Edgebinder 45x195 C24 @ 4.8m; 45x59 rips 3 per 45x195 (3mm kerf).
P-09 | Waist band ripped from 1197x2397 9mm OSB/3, 4 x 290 strips per sheet.
P-10 | Breather 100m x 2.7m rolls; 450 strips cut off the roll (~222 per roll); one line with panel breather.
P-11 | Nails 3 x 90 ring-shank per joint / noggin end, multi-ply @150 staggered (both sides > 2 ply, 3 lots > 3 ply), boxes 2,500. OSB: 3.1x50 coil nails @150 edges / 300 field, boxes 2,500 (P-11a). No VCL, no mineral wool. PIR 120 to external walls only.
P-15 | One 2.7m 4x1 brace per panel joint on EX / IL / gable panels; 600 38x89 noggin each.
P-16 | Window battens 38x43 from 38x89 C16 ripped in half, external openings only.
P-21 | Brick ties 3.7/m2 net external wall area (GF + FF + gables less openings) +10%, boxes of 250.
P-22 | Steel beams are TLS supply.
D-17 | Head binder on external and load-bearing walls only.
Acorn | Metal-web joists, hangers, strongbacks, noggins and roof trusses / cut roof by Acorn Timber Engineering - not in TLS procurement.